SDoH - Structural Intervention Action Plan - Simplified Guide

Purpose

Use this action plan to design structural interventions that address social determinants of health (SDoH). The plan outlines goals, measurable objectives, and specific activities needed to create systems-level change.

- Goal Statement

Write one broad statement describing what you want to change and how you will achieve it.

Format:

To (what you want to improve) by (overall approach you will take).

- Objectives

Objectives should be SMART (specific, measurable, achievable, relevant and time-bound) and describe what will change as a result of your intervention.

- Indicators

List what you will measure to show progress or confirm change has occurred.

- Communication Plan

Identify who you need to reach, why, and how you will communicate.

- Activities

List the step-by-step actions needed to achieve each objective.

- Timeframe

Assign a start and end date for each activity.

- Required Resources

List what you need to complete each activity.

- Lead

Identify the person responsible for each activity.

- Anticipated Products or Results

State the expected output for each activity.

# Example: Structural Intervention Addressing HIV-Related Stigma

## GOAL STATEMENT:

To reduce HIV-related stigma in community healthcare settings by implementing staff training, community education, and anti-discrimination policies.

## Objective #1:

By Dec 31, 2026 all clinic staff at three partner sites will complete HIV stigma-reduction training.

### Indicators:

- Number of staff completing training

- Pre/post training stigma scores

- Staff adoption of affirming communication practices

### Communication Plan:

Target: Clinic leadership, frontline staff

Purpose: Promote adoption and support for stigma-reduction training

Approach: Meetings, email updates, informational flyers

### Activities Table

| Activity | Timeframe | Resources Needed | Lead | Expected Result | Completion Date |
| --- | --- | --- | --- | --- | --- |
| Develop stigma-reduction curriculum | July–Aug | Training team, curriculum materials | Training Coordinator | Curriculum completed | Aug 31, 2026 |
| Deliver training sessions | Sept –Dec | Trainers, space, evaluation tools | Training Team | Staff trained | Dec 31, 2026 |

Action Plan Template

## GOAL STATEMENT:

______________________________________________________________

### Objective #1:

______________________________________________________________

### Indicators:

-

-

### Communication Plan:

Target:

Purpose:

Approach:

### Activities Table #1

| Activity | Timeframe | Resources Needed | Lead | Expected Result | Completion Date |
| --- | --- | --- | --- | --- | --- |

### OBJECTIVE #2:

______________________________________________________________

### Indicators:

-

-

### Communication Plan:

Target:

Purpose:

Approach:

### Activities Table #2

| Activity | Timeframe | Resources Needed | Lead | Expected Result | Completion Date |
| --- | --- | --- | --- | --- | --- |